Milestones to achieve to support the financial forecasts produced for 2021 – 2022

| Area | By 30 Jun | By 31 Jul | By 31 Aug | By 30 Sep |
| --- | --- | --- | --- | --- |
| - Existing services/offerings | All clear, in place & operational | Reviewed and adjusted if necessary | Reviewed and adjusted if necessary | Reviewed and adjusted if necessary |
|  |  | 100% Occupancy targets met | 100% Occupancy targets met | 100% Occupancy targets met |
|  | All pricing reviewed and adjusted on all sites/literature | Pricing feedback sought & analysed | Pricing feedback sought & analysed | Pricing feedback sought & analysed |
|  | Income min £1500 pm | Income min £2000 pm | Income min £2,000 pm | Income min £1500 pm |
| - New services/offerings or collaborations | Consider potential new services or extras | Consider potential new services or extras | Consider potential new services or extras | Consider potential new services or extras |
|  | Identify potential collaborative opportunities |  |  |  |
| - Customers | Customer Survey drafted and issued | Customer Survey in operation | Customer Survey in operation | Customer survey completed |
|  |  |  |  | Customer survey findings analysed |
|  |  |  |  | Survey Action Plan drawn up |
|  | 10 Google Reviews sought & followed up | 10 Google Reviews sought & followed up | 10 Google Reviews sought & followed up | 10 Google Reviews sought & followed up |
| - Web Presence | All booking sites fully reviewed for photos, brand, text etc. | All problems fixed and brand/messages aligned fully |  |  |
|  | Google presence & all Google details checked: (Opening hours; services; photos etc.) | Google presence & all Google details checked: (Opening hours; services; photos etc.) | Google presence & all Google details checked: (Opening hours; services; photos etc.) | Google presence & all Google details checked: (Opening hours; services; photos etc.) |
|  | Website fully reviewed | Website critical updates completed – photos; reviews etc. |  |  |
| - Marketing/Social Media | AdWords £100 Spend v Return target met….. | AdWords £100 Spend v Return target met | AdWords £100 Spend v Return target met | AdWords £100 Spend v Return target met |
|  | Emails captured for all customers | Emails captured for all customers | Emails captured for all customers | Emails captured for all customers |
|  | Email newsletter issued with updates and special offers | Email newsletter issued with updates and special offers | Email newsletter issued with updates and special offers | Email newsletter issued with updates and special offers |
|  | Develop a social media calendar & implement | Implement social media calendar | Implement social media calendar | Implement social media calendar |
| - Competitors | 5x main competitor identified & Strengths/weaknesses listed | Lessons learned & messages amended to highlight our USP | Competitor reviews read and actions taken | Competitor reviews read and actions taken |
| - Overall Sales Income | Income min £1500pm | Income min £2000 pm | Income min £2,000 pm | Income min £1500 pm |
| - Overall Costs | Total costs (exc. Staff) £XX | Total costs (exc. Staff) £XX | Total costs (exc. Staff) £XX | Total costs (exc. Staff) £XX |
| - Key Individual Costs | All reviewed and cost savings identified | All reviewed and cost savings identified | All reviewed and cost savings identified | All reviewed and cost savings identified |
| - Profit | Net Profit min £1200 | Net Profit min £1700 | Net Profit min £1700 | Net Profit min £1200 |
| - Other….. |  |  |  |  |

| Actions | Who? | By Date |
| --- | --- | --- |
|  |  | 30 Sep 2021 |
|  |  | 31 Oct 2021 |